## Sheet1
Dates are different because those are the date we had our meetings
CTRL + ENTER = New line
| Date | Attendees | What you have done so far | What you want to do next | Additional Notes/Points to consider
| 2025-02-04 | Rawad | - Researched about what Resole are as an organisation | With knowledge of the organisation, start writing the introductuon
|  | Mo | - read the additional documents from blackboard - to have background knowledge about the project and business | Do more research about how the business works and check the website related
|  | Mourad | - Planning questions for the interview with resole with depened understanding of Resole objectives via reading the brief and watching video | - Start with a draft introduction of Resole with infomation gained from the interview
|  | Bhavjot | - The Google drive was created, I created the interview file where we can put all our questions so we can decide on final question to ask the person from Resole - Secondly, While researching create my own intro as well & think of the next task (Planning) which has been assigned to me | Conduct research about resole to support others for their introductions To Do: Start finding questions and gather other questions from group members and create an overview for it.
|  | Kel | - Formulated 2 questions for interview - Created Shared drive for all documentation for the group -Read documentation to get a better understanding of Resole and their objectives
| 2025-02-06 | Rawad | - Progress in writing the introduction, whilst outlining the objectives to be completed | - Forumulate 2 questions for the interview, - Finish the introduction for the initial report
|  | Mo | - had more than a basic knowledge about the data and documents that been shared in blackboard | - Finalise some questions that needed to be ask in the interview
|  | Mourad | - Clarified my understanding by reading through my and group's notes of interview | - Complete the Introduction - Have questions ready for the interview
|  | Bhavjot | - Completed my own Introduction and created this meeting minutes plan - Meeting minutes plan is created to ensure which person has done what task - I also created a table structure was created for all the questions and a notes section to write all the notes from the interview meetings | - Start the Planning task in the mark scheme
|  | Kel | - Discussed plans for meeting dates in the future (Wednesdays) | -Locate Data sets -Create a draft introduction
| 2025-02-14 | Rawad | - Completed the introduction for the initial draft report | - Oversee data collection task, Complete Flowchart for Report | - Unable to attend the interview
|  | Mo |  | - look for a dataset
|  | Mourad | - Completed draft introduction | -Review datasets provided
|  | Bhavjot | - A quick checkup on everyone and their progess, and an initial draft report was created - Also, created a gantt chart | - Support Rawad in his final introduction and planning to get a review from the lecturer before submitting initial draft report. | - Regularly updating the meeting minutes and planning the next meetings
|  | Kel | Completed draft introduction | -Locate Data sets
| 2025-02-17 | Rawad | N/A | N/A
|  | Mo | ------ | ------
|  | Mourad | N/A | N/A | Unable to attend meeting
|  | Bhavjot | - Got a review from the lecturer about our progress | - Need to assign tasks properly, and tasks and We have to have risk assessment, contingency plan, go back to marking scheme | The reviews had been taken and Bhavjot and Rawad did a meeting to make those changes in the Initial Draft Report and Gantt Chart
|  | Kel |  |  | Unable to attend meeting
| 2025-02-18 | Rawad | Completed Flowchart | - Check the datasets and help decide which ones to use for further cleaning
|  | Mo | gathering some primary datasets | - check the datasets and find more potentials - try to choose between datasets(find useful one's with reason) - write down the process of collection and problems i faced
|  | Mourad | -Looked over datasets and knowing which ones to use and their purpose | - Once datasets are collected and approved from group I will begin in the cleaning of the data
|  | Bhavjot | Created a new initial draft report and gantt chart | - Once the datasets are created, help mourad with data cleaning. - To do: Conduct a meeting on 20th Feb to check the progess
|  | Kel | - Located 3 x primary datasets - Updated new meeting minutes with my tasks | - Create list of dates for everything i have done - Re-write my old meeting minutes to new meeting minutes doc
| 2025-02-20 | Rawad | - Look over colleted datasets once all have been compiled. | - Provide feedback on datasets and recommend which datasets use for further analysis
Mo
|  | Mourad | - Understanded the other datasets provided | - Will look over collected datasets and plan ahead of the processes needed to clean it - Clean datasets provided and help Bhavjot with the dashboard
|  | Bhavjot | Completed creating the planning phase from the mark scheme, WBS, Project deliverables, Risk and mitigation plan Completed creating roles and responsibilities. Also, Created a Mark scheme checklist | Decide on the datasets (Which ones to use, as in which ones are beneficial)
|  | Kel | - Created list of dates for everything i have done so far, along with evidence (ongoing) -Re-wrote my old meeting minutes to new meeting minutes doc | - Locate more data sets - Create a Kanban board for project management - Organise Google drive to have a coherent file structure
| 2025-02-25 | Rawad | -Reviewed Feedback given from Lecturers | - Planned Next steps (When to do presentation & Cleaning datasets for EDA)
|  | Mo | - Filling the dataset file about the sources and the reason they have been chosen
|  | Mourad | - Debreifed with the group in what datsets i will like to use and got their oppinions in how to clean them - Already started with a bit of cleaning of a dataset of my choosing and got it approved from group | - If any other datasets are of worth i will debreif with my group members and ask how we will like it cleaned
|  | Bhavjot | - Mourad helped choosing the datasets | - Help with submitting the Initial draft report - Start the cleaning process with Mourad and Rawad | We were mainly looking for datasets and deciding which datasets to use, and helping them giving it a start for the data phase in the initial draft report
|  | Kel | - Started initial cleaning on Resole data set , with Python - Created Kanban board for planning with team - Updated Kanban board with marking scheme and started allocating tasks to users - Organized google drive - Created file and wrote the sources out for all my data sets and explained why they were chosen | - Write info about data sets sourced, on the final report -Review Final report for issues / required changes - Upload report
Initial Draft Report Submission | 2025-02-26 | Rawad
Mo
|  | Mourad | - Reviewed the draft and specification before submission of intital draft | - Started with data cleaning for resole data
|  | Bhavjot | - Reviewing the initial draft report and Kel is the one submitting it.
Kel
| 2025-03-11 | Rawad | -EDA / Cleaning a dataset as well as provide data visualisations for analysis - Discussed clustering model - Began Analysis of EDA (In relation to the draft project report for the client) | - Carry on with EDA and cleaning - Get started on the presentation - Begin Analysis of EDA
|  | Mo | - Discussed clustering model | - start looking at creating the clustering model
|  | Mourad | -EDA / Cleaning - Discussed clustering model | -Finish resole cleaning and assit Rawad if required with the dataset avaliable
|  | Bhavjot | - Logged feedback for meeting with Phil - Discussed clustering model | - Change up the report to include revised work tasks | Also, re-creating the gantt chart from dates to weeks.
|  | Kel | - setup Git repository , uploaded all documents so far , and shared with group -Submitted initial draft report | - push meeting minutes to GIT - Review Mourads code -Assist others where needed
| 2025-03-18 | Rawad
Mo
|  | Mourad | - Finished cleaning Resole provided database | - Awaiting Kelvin review of completed code of data cleaning for resole database
|  | Bhavjot | - Completing the WBS halfway without the time plan with Kelvin's help, and got feedback for Gantt chart - Started working on Dashboard for visualisations | - Revise the gantt chart, make the tasks simpler and change the dates to weeks. | visualisations are also used for presentations and not just help other for EDA
Kel
| 2025-03-19 | Rawad | -Completed EDA analysis for my dataset & visualisations | - Begin Presentation slides
Mo
|  | Mourad | -Completed the cleaning for the LA dataset and given ideas on what visulisations we can use | - Review Bhavjot changes to the report - Awaiting for second review for kelvin as i fixed the punctuation and grammer for the employment_status column
|  | Bhavjot | - Completed WBS time plan - Completed Gantt chart - Completed creating a Dashboard - Updated my meeting minutes | - Get feedback from peers and make changes to dashboard or Gantt chart
Kel
Client Draft Report Submission | 2025-03-20 | Rawad | -Reviewed Dashboard - Oversaw Initial Draft Report Submission. | -Begin Presentation Slides
Mo
|  | Mourad | - Clean datasets provided and help Bhavjot with the dashboard
|  | Bhavjot | - Updated the Dashboad with a new cleaned dataset and made changes based on the feedback - Uploaded the work on Github
Kel
| 2025-03-23 | Rawad | - Providing Recommendations in the Presentation for Resole
|  | Mo | - Create Homelessness distribution charts as well as for asylum seekers | - Add a map for homlessness distribution, line charts for asylum seekers by region and around the country.
|  | Mourad | - Providing suggestions and changes for the presentation
|  | Bhavjot | - Created Presentation with Rawad - Added screenshot of graphs
|  | Kel | - Providing suggestions and changes for the presentation
Live Client Presentation | 2025-03-24 | Rawad
|  | Mo | - Submitting it during the morning in the next meeting
|  | Mourad | - looked over notes on improvements provided by lecturers and started planning on making improvments | - Start with individual report
|  | Bhavjot | - Got feedback and suggesting changes that needs to be made on the report | - Add the Github and Google drive link in the report and upload the main file to Github
|  | Kel | - Made notes on suggested changes | - Implement feedback to the report
| 2025-03-26 | Rawad | - Made the presentation (With the help of group) | - Act on the advice given from lecturers for the draft report and complete report
|  | Mo | - Got feedback and cleaning the report and making it look presentable by adding map, regression model, and graphs
|  | Mourad | - I was able to create a regression model for assylum seekers with the help of my group and recieved feeback on my code once completed | - Finish individual report
|  | Bhavjot | - Started working on the individual report | - Conduct a quick checkup on everyone to see if everything is correct | - By checking it means the report
|  | Kel | - Decided final roles to finish report | Will make report changes to implement suggested changes
Final Project Report Submission | 2025-02-02 | Kel | The group coursework was submitted by the group leader, and then individual reflection reports are submitted individually